## GWMv2 ADAS plan
ADAS development plan to Customer GWMv2MH
ID | Items | User Story | Owner | MAN/DAY | 2017-05-01 |  |  |  | 2017-06-01 |  |  |  |  | 2017-07-01
[5 empty] | w18 | w19 | w20 | w21 | w22 | w23 | w24 | w25 | w26 | w27 | w28 | w29 | w30 | w30
[5 empty] | 5.1~5.5 | 5.8~5.12 | 5.15~5.19 | 5.22~5.26 | 5.29~6.2 | 6.5~6.9 | 6.12~6.16 | 5.19~6.23 | 6.26~6.30 | 7.3~7.7 | 7.10~7.14 | 7.17~7.21 | 7.14~7.28 | 7.14~7.28
Feature FO
GWMFRS_1_1_1 | RVC | CRS-FRS | Wang Xiaole | 4 | 2017-05-01 w20: 0.2; 2017-05-01 w21: 0.2; 2017-06-01 w22: 0.2; 2017-06-01 w23: 0.2
GWMFRS_1_1_2 |  | HDD | Wang Xiaole | 2 | 2017-06-01 w24: 0.2; 2017-06-01 w25: 0.2
GWMFRS_1_2_1 | SVC | CRS-FRS | Wang Xiaole | 4 | 2017-05-01 w20: 0.2; 2017-05-01 w21: 0.2; 2017-06-01 w22: 0.2; 2017-06-01 w23: 0.2
GWMFRS_1_2_2 |  | HDD | Wang Xiaole | 2 | 2017-06-01 w24: 0.2; 2017-06-01 w25: 0.2
GWMFRS_1_3_1 | AVM | CRS-FRS | Lu Guofeng | 6 | 2017-05-01 w20: 0.3; 2017-05-01 w21: 0.3; 2017-06-01 w22: 0.3; 2017-06-01 w23: 0.3
GWMFRS_1_3_2 |  | HDD | Lu Guofeng | 3 | 2017-06-01 w24: 0.3; 2017-06-01 w25: 0.3
GWMFRS_1_4_1 | MOD | CRS-FRS | Lu Guofeng | 6 | 2017-05-01 w20: 0.3; 2017-05-01 w21: 0.3; 2017-06-01 w22: 0.3; 2017-06-01 w23: 0.3
GWMFRS_1_4_2 |  | HDD | Lu Guofeng | 3 | 2017-06-01 w24: 0.3; 2017-06-01 w25: 0.3
GWMFRS_1_5_1 | PAS | CRS-FRS | Li Hui | 4 | 2017-05-01 w20: 0.2; 2017-05-01 w21: 0.2; 2017-06-01 w22: 0.2; 2017-06-01 w23: 0.2
GWMFRS_1_5_2 |  | HDD | Li Hui | 2 | 2017-06-01 w24: 0.2; 2017-06-01 w25: 0.2
GWMFRS_1_6_1 | APA | CRS-FRS | Shan JianChao | 6 | 2017-05-01 w20: 0.3; 2017-05-01 w21: 0.3; 2017-06-01 w22: 0.3; 2017-06-01 w23: 0.3
GWMFRS_1_6_2 |  | HDD | Shan JianChao | 3 | 2017-06-01 w24: 0.3; 2017-06-01 w25: 0.3
GWMFRS_1_7_1 | Vendor interface |  | Lu Guofeng | 60 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
2 | System Dependency
GWMFRS_2_1_1 | Hardware platform | Target bringup | Huang Xiaowen
GWMFRS_2_2_1 | Camera device, ECU etc. | rear camera;right camera,left camera, front camera, PAS,APA ECU | GWM
GWMFRS_2_3_1 | Capture/Display Driver | Intel firmware | Intel
GWMFRS_2_3_2 |  | BSP | Huang Xiaowen
GWMFRS_2_3_3 |  | V4L2 | Huang Xiaowen
GWMFRS_2_3_4 |  | G2D | Huang Xiaowen
GWMFRS_2_3_5 |  | Weston | Huang Xiaowen
GWMFRS_2_4_1 | Car Input | CAN | Li Rongliang
GWMFRS_2_4_2 |  | GPIO | Huang Xiaowen
GWMFRS_2_4_3 |  | PowerMode | Wu Jing
GWMFRS_2_4_4 |  | EOL | Wu Jing
GWMFRS_2_5_1 | HMI Input | HMI | GuoWeiwei
GWMFRS_2_6_1 | Layer Manager | Camera layer/Graphic layer | Chen Huichao
GWMFRS_2_7_1 | Achitecher | Early RVC | System/Wang Xiaole | 40 | 1 | 1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
3 | Algrithm Core
GWMFRS_3_1_1 | Image Quality |  | CoC ADAS
GWMFRS_3_1_2 | Around View camera |  | CoC ADAS
GWMFRS_3_1_3 | Auto Calibration |  | CoC ADAS
GWMFRS_3_1_4 | MOD |  | CoC ADAS
GWMFRS_3_1_5 | Dynamic guide line |  | Shan Jianchao/lin nan | 50 | 2017-05-01 w21: 0.7; 2017-06-01 w22: 0.7; 2017-06-01 w23: 0.7; 2017-06-01 w24: 0.7; 2017-06-01 w25: 0.7; 2017-06-01 w26: 0.2; 2017-07-01 w27: 0.2
4 | Appliction Core
GWMFRS_4_1_1 | ADAS Module Mananger | module life cycle(IPC,Diagnorsis) | Wang Xiaole | 20
GWMFRS_4_1_2 |  | module event dispatcher | Wang Xiaole | 10 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
GWMFRS_4_1_3 |  | module event after handler | Wang Xiaole | 10 |  |  |  | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
GWMFRS_4_2_1 | IPC Mananger | IPC API(project use) | Wang Xiaole | 20 |  |  |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 | 0.4 | 0.3 | 0.3 | 0.3 | 0.1
GWMFRS_4_2_2 |  | IPC adptor | Wang Xiaole | 20
GWMFRS_4_2_3 |  | porting with Common API | Wang Xiaole | 20 |  |  |  | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
GWMFRS_4_2_4 |  | porting with Case Client | Lu Guofeng | 20 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
GWMFRS_4_3_1 | Camera HUB module | camera Hub API | Li Hui | 10 |  |  |  | 0.2 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
GWMFRS_4_3_2 |  | multi-Camera state machine | Li Hui | 20 |  |  |  | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
GWMFRS_4_3_3 |  | priority management | Li Hui | 10
GWMFRS_4_3_4 |  | override management | Li Hui | 10
GWMFRS_4_4_1 | Camera abtract module | camera API | Li Hui | 10 |  |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
GWMFRS_4_4_2 |  | camera state machine | Li Hui | 20 | 0.1 | 0.1 | 0.1 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
GWMFRS_4_5_1 | APA abstract module | APA API | Shan JianChao | 10 | 2017-06-01 w26: 0.2; 2017-07-01 w27: 0.2; 2017-07-01 w28: 0.2; 2017-07-01 w29: 0.2; 2017-07-01 w30: 0.2; 2017-07-01 w30: 0.2
GWMFRS_4_5_2 |  | APA state machine | Shan JianChao | 20 | 2017-06-01 w26: 0.2; 2017-07-01 w27: 0.2; 2017-07-01 w28: 0.2; 2017-07-01 w29: 0.2; 2017-07-01 w30: 0.2; 2017-07-01 w30: 0.2
GWMFRS_4_6_1 | PAS abstract module | PAS API | Li Hui | 10
GWMFRS_4_6_2 |  | PAS state machine | Li Hui | 20
GWMFRS_4_7_1 | Diagnosis | Dianosis API | Lu Guofeng | 5
GWMFRS_4_7_2 |  | Dianosis state machine | Lu Guofeng | 10
GWMFRS_4_8_1 | AVM abstract module | AVM API | Lu Guofeng | 5
GWMFRS_4_8_2 |  | AVM state machine | Lu Guofeng | 20
GWMFRS_4_9_1 | Command line |  | Shan Jianchao | 10 | 2017-07-01 w28: 0.1; 2017-07-01 w29: 0.1; 2017-07-01 w30: 0.1; 2017-07-01 w30: 0.1
GWMFRS_4_10_1 | Functional safe module | camera frezee | Lu Guofeng | 10
GWMFRS_4_10_2 |  | Heart beat | Lu Guofeng | 10
GWMFRS_4_11_1 | Message & DataType |  | ALL
GWMFRS_4_12_1 | Driver Manager | driver manager moudle | Wang Xiaole | 10 | 2017-07-01 w30: 0.1
GWMFRS_4_12_2 |  | layer management | Wang Xiaole | 20 | 2017-07-01 w30: 0.1
GWMFRS_4_12_3 |  | capture driver API | Li Hui | 20
GWMFRS_4_12_4 |  | grphic driver API | Shan Jianchao | 20 | 2017-07-01 w28: 0.3; 2017-07-01 w29: 0.3; 2017-07-01 w30: 0.3; 2017-07-01 w30: 0.3
GWMFRS_4_13_1 | Use case module |  | Lu Guofeng | 30
GWMFRS_4_14_1 | Capture.lib | capture drive API/thread | Wang Xiaole | 20
GWMFRS_4_15_2 | Graphic lib | graphic shell(EGL),rendering | Shan Jianchao/lin nan | 30 | 2017-06-01 w26: 0.4; 2017-07-01 w27: 0.4; 2017-07-01 w28: 0.2; 2017-07-01 w29: 0.2; 2017-07-01 w30: 0.2; 2017-07-01 w30: 0.2
| Foundation lib | base line | Lu Guofeng | 10 | 2017-05-01 w18: 0.4; 2017-05-01 w19: 0.4; 2017-05-01 w20: 0.4; 2017-05-01 w21: 0.4; 2017-06-01 w22: 0.4
GWMFRS_4_16_1 |  | Thread,Queue,Event,State,... etc | ALL | 30
| CaseClient lib | deamon | Lu Guofeng | 10
|  | api mode | Lu Guofeng | 10
GWMFRS_4_17_1 |  | dbus mode | Lu Guofeng | 10 |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
5 | Application (GWMV2 Use Case)
GWMFRS_5_1_1 | Rear View System | Rear camera FIDL | Wang Xiaole | 5 | 2017-07-01 w28: 0.1; 2017-07-01 w29: 0.1; 2017-07-01 w30: 0.1; 2017-07-01 w30: 0.1
GWMFRS_5_1_2 |  | 6.5.8.1 RVC image display | Wang Xiaole | 20
GWMFRS_5_1_3 |  | 6.5.8.2.1 Warning message display | Wang Xiaole | 20
GWMFRS_5_1_4 |  | 6.5.8.2.2 Trunk open reminder | Wang Xiaole | 20
GWMFRS_5_1_5 |  | 6.5.8.2.3 Trailer mode reminder | Wang Xiaole | 20
GWMFRS_5_1_6 |  | 6.5.8.3 Popup & Notification handling on RVC | Wang Xiaole | 10
GWMFRS_5_1_7 |  | 6.5.8.4 Application switching on RVC | Wang Xiaole | 30
GWMFRS_5_1_8 |  | Guide line view | Wang Xiaole | 20
GWMFRS_5_1_9 |  | camera caputure | Wang Xiaole | 10
GWMFRS_5_1_10 |  | on site calibration | Wang Xiaole | 5
GWMFRS_5_1_11 |  | Diagnosis: rear camera | Wang Xiaole | 20
GWMFRS_5_2_1 | Side View System | Side camera FIDL | Wang Xiaole | 5
GWMFRS_5_2_2 |  | 6.5.11.1 activation/deactivation | Wang Xiaole | 20
GWMFRS_5_2_3 |  | 6.5.11.2.1 Speed limits | Wang Xiaole | 10
GWMFRS_5_2_4 |  | 6.5.11.2.2 Warning message display | Wang Xiaole | 10
GWMFRS_5_2_5 |  | Diagnosis: side camera | Wang Xiaole | 20
GWMFRS_5_3_1 | Around View System | Around camera FIDL | Lu Guofeng | 5
GWMFRS_5_3_2 |  | 6.5.12.1 AVM activation/deactivation | Lu Guofeng | 20
GWMFRS_5_3_3 |  | 6.5.12.2 Guidelines for parking setting | Lu Guofeng | 20
GWMFRS_5_3_4 |  | 6.5.12.3 Radar sensors display&distance detection | Lu Guofeng | 20
GWMFRS_5_3_5 |  | 6.5.12.4 Speed limits of AVM deactivation | Lu Guofeng | 10
GWMFRS_5_3_6 |  | 6.5.12.5 Warning message display | Lu Guofeng | 10
GWMFRS_5_3_7 |  | 6.5.12.6 Warning message display-Fault | Lu Guofeng | 10
GWMFRS_5_3_8 |  | 6.5.12.7 Change view modes | Lu Guofeng | 20
GWMFRS_5_3_9 |  | 6.5.12.8 Popup & Notification on AVM | Lu Guofeng | 5
GWMFRS_5_3_10 |  | 6.5.12.9 Application switching on AVM | Lu Guofeng | 5
GWMFRS_5_3_11 |  | 6.5.12.10.1 Other Display:"Door open reminder" | Lu Guofeng | 10
GWMFRS_5_3_12 |  | 6.5.12.10.2 Other Display:"Trunk open reminder" | Lu Guofeng | 10
GWMFRS_5_3_13 |  | 6.5.12.10.3 Other Display:"Outside mirror folded reminder" | Lu Guofeng | 10
GWMFRS_5_3_14 |  | on site calibration | Lu Guofeng | 10
GWMFRS_5_3_15 |  | Diagnosis: around camera | Lu Guofeng | 20
GWMFRS_5_4_1 | MOD System | MOD FIDL | Lu Guofeng | 5
GWMFRS_5_4_2 |  | MOD View(Front/Rear) | Lu Guofeng | 30
GWMFRS_5_4_3 |  | Diagnosis: MOD | Lu Guofeng | 10
GWMFRS_5_5_1 | AutoCalibration System | AutoCalibration FIDL | Lu Guofeng | 5
GWMFRS_5_5_2 |  | AutoCalibration View | Lu Guofeng | 20
GWMFRS_5_5_3 |  | Diagnosis: AutoCalibration | Lu Guofeng | 10
GWMFRS_5_6_1 | PAS System | PAS FIDL | Li Hui | 15
GWMFRS_5_6_2 |  | 6.5.9.1.1 PAS activation/deactivation | Li Hui | 25
GWMFRS_5_6_3 |  | 6.5.9.1.2 RPAS information display | Li Hui | 25
GWMFRS_5_6_4 |  | 6.5.9.1.3 FPAS information display | Li Hui | 25
GWMFRS_5_6_5 |  | 6.5.9.2 APA information display | Li Hui | 25
GWMFRS_5_6_6 |  | 6.5.9.3 Voice announcement | Li Hui | 25
GWMFRS_5_6_7 |  | 6.5.9.4.1 Error/Exception handling in automatic PAS | Li Hui | 10
GWMFRS_5_6_8 |  | 6.5.9.4.2 Warning message display | Li Hui | 10
GWMFRS_5_6_9 |  | Diagnosis: PAS | Li Hui | 20
GWMFRS_5_7_1 | APA System | APA FIDL | Shan Jianchao | 5
GWMFRS_5_7_2 |  | 6.5.10.1 "Parallel parking | Shan Jianchao | 20
GWMFRS_5_7_3 |  | 6.5.10.2 "Perpendicular parking | Shan Jianchao | 20
GWMFRS_5_7_4 |  | 6.5.10.3 "Valet parking | Shan Jianchao | 20
GWMFRS_5_7_5 |  | Diagnosis: APA | Shan Jianchao | 20
GWMFRS_5_8_1 | ADAS Configuration | Command line | Shan Jianchao | 10
GWMFRS_5_8_2 |  | EOL Configuration | Shan Jianchao | 10
GWMFRS_5_9_1 | Diagnorsis | Diagnorsis FIDL | Lu Guofeng | 5
GWMFRS_5_9_2 |  | Diagnorsis Manager | Lu Guofeng | 20
GWMFRS_5_10_1 | ADAS Moudle Manager | GWMv2 ADAS Manager state machine | Wang Xiaole | 30
GWMFRS_5_10_1 |  | GWMv2 ADAS system event dispatcher | Wang Xiaole | 20
GWMFRS_5_10_1 |  | GWMv2 ADAS system event pre-dispatcher | Wang Xiaole | 20
GWMFRS_5_11_1 | Car Input Module | External input from user/system | Wang Xiaole | 30
GWMFRS_5_12_1 | KPI/Performance | early camera | Wang Xiaole | 40
GWMFRS_5_12_2 |  | RVC/SVC switching | Wang Xiaole | 20
GWMFRS_5_12_3 |  | AVM switching | Lu Guofeng | 20
GWMFRS_5_12_4 |  | PAS overlay | Lu Guofeng | 10
GWMFRS_5_12_5 |  | Guide line overlay | Lu Guofeng | 10
6 | Integration & Testing
GWMFRS_6_1_1 | RVC road test |  | Wang Xiaole | 5
GWMFRS_6_1_2 | SVC road test |  | Wang Xiaole | 5
GWMFRS_6_1_3 | AVM road test |  | Lu Guofeng | 10
GWMFRS_6_1_4 | MOD road test |  | Lu Guofeng | 10
GWMFRS_6_1_5 | PAS road test |  | Li Hui | 5
GWMFRS_6_1_6 | APA road test |  | Shan Jianchao | 5
| Manpower |  |  |  | 2017-05-01 w18: 0

## CoC workPackages-SV
Product | Category | User Story | WP | Estimate (MDs) |  | Confidence | Remarks
|  |  |  | Normal | WCS
SV | Online calibration - Core | Core - Calibration Pipeline Integration | Calibration Architecture | 7 | 12 | Medium | GWMFRS_3_1_3
|  |  | Calibration Integration | 10 | 15 | Medium
|  |  | Calibration Performance optimization | 20 | 35 | Low
|  |  | Data collection and annotation | 15 | 25 | Medium
|  |  | Testing and debugging | 15 | 30 | Low
|  | APP - Calibration State machine | Activation logic requirements analysis | 5 | 7 | High | GWMFRS_5_5
|  |  | Calibration State machine architecture | 5 | 7 | High
|  |  | Calibration State machine development | 15 | 22 | High
|  |  | Testing & Debugging | 10 | 15 | High
| View Generation | Core - 3D - Surround View Integration | View generation requirements setup | 10 | 15 | High | GWMFRS_3_1_2
|  |  | View generation adaptions/Configurations | 22 | 35 | High
|  |  | Performance optimizations | 22 | 35 | High
|  |  | Testing | 20 | 30 | High
|  | APP - View State Machine | View State Machine Requirements | 7 | 10 | High | GWMFRS_4_7
|  |  | View State Machine architecture | 7 | 10 | High
|  |  | View State machine Development | 15 | 22 | High
| Early Video | Early Video architecture | System architecture setup | 20 | 40 | Low | GWMFRS_2_7_1
|  |  | SoC specific configuration/development | 20 | 40 | Low
|  |  | Applications Adaptions | 20 | 40 | Low
|  |  | Integration | 20 | 40 | Low
|  |  | Testing | 10 | 20 | Low
| Image quality | Image quality analysis setup | Image quality requirements | 10 | 15 | High
|  |  | Image quality algorithms tuning/Configuration | 15 | 20 | High
|  |  | Data collection and annotation | 15 | 25 | High
|  |  | Testing and debugging | 10 | 15 | High
|  | Camera Backchannel control | Camera requirements analysis | 5 | 8 | High
|  |  | Camera control integration | 10 | 17 | High
|  |  | Testing & Debugging | 7 | 12 | High
| Application Layer | Interface Development | CAN Interfaces | 7 | 12 | High | GWMFRS_2_4_1
|  |  | HMI Interfaces | 15 | 25 | Low | GWMFRS_2_5_1
|  |  | Diagnostics interfaces | 7 | 12 | High | GWMFRS_2_4_3
|  |  | LC Interfaces | 7 | 12 | High | GWMFRS_2_4_4
|  | Video WD | Safety Concept requirements | 7 | 10 | High
|  |  | Video WD Architecture | 10 | 15 | High
|  |  | Video WD Implementation | 15 | 22 | High
|  |  | Core Adaptions | 15 | 22 | High
|  |  | Testing & Debugging | 10 | 15 | High
|  | Error Handler | Error Handling requirements | 5 | 8 | High
|  |  | Error Handling architecture | 5 | 8 | High
|  |  | Error handling implementation | 15 | 20 | High
|  |  | Testing & Debugging | 10 | 15 | High
| Generic | Testing | Test environment definition | 5 | 8 | High
|  |  | Test setup | 15 | 22 | High
|  |  | Test plan development | 7 | 12 | High
|  |  | Test cases definition | 15 | 22 | High
|  | Architecture & Requirements | TRS setup | 15 | 22 | High
|  |  | HLD Development | 15 | 22 | High
|  |  | Sum | 567 | 921

## CoC workPackages-MOD
Product | Category | User Story | WP | Estimate (MDs) |  | Confidence | Remarks
|  |  |  | Normal | WCS
MOD | MOD Core Integration | Core - MOD Pipeline Development | MOD Architecture | 15 | 30 | Low
|  |  | MOD Pipeline development - PC | 45 | 70 | Low
|  |  | Target Integration | 30 | 60 | Low
|  |  | Performance optimizations | 30 | 60 | Low
|  |  | Testing and debugging | 25 | 40 | Low
|  | APP - MOD | Activation logic requirements analysis | 15 | 25 | Medium
|  |  | MOD State machine architecture | 10 | 18 | High
|  |  | MOD State machine development | 15 | 22 | High
|  |  | Interface adaptions | 10 | 25 | Low
|  |  | Testing & Debugging | 15 | 25 | High
| Fusion - Radar Data | Radar Feature Processing | Architecture | 15 | 25 | Low
|  |  | Radar Feature interface | 15 | 25 | Low
|  |  | Radar Feature filtering | 22 | 35 | Low
|  |  | Integration | 15 | 25 | Low
|  |  | Testing & Debugging | 20 | 30 | Low
|  | MAP Fusion | Architecture | 10 | 20 | Low
|  |  | Vision Map features input | 10 | 18 | Low
|  |  | Radar map features input | 10 | 18 | Low
|  |  | MAP Data fusion | 22 | 35 | Low
|  |  | Integration | 22 | 45 | Low
|  |  | Testing & Debugging | 15 | 35 | Low
| MOD Core Development | MOD Prototype | Architecture | 40 | 80 | Low
|  |  | Algorithm prototyping | 100 | 150 | Low
|  |  | Algorithms Core pipeline setup | 160 | 250 | Low
|  |  | Data collection and annotation | 60 | 100 | Low
|  |  | Testing | 40 | 100 | Low
| Generic | Testing | Test environment definition | 22 | 35 | Low
|  |  | Test setup | 22 | 35 | Low
|  |  | Test plan development | 10 | 20 | Low
|  |  | Test cases definition | 20 | 35 | Low
|  | Architecture & Requirements | TRS setup | 15 | 25 | Low
|  |  | HLD Development | 15 | 25 | Low
|  |  | Total | 890 | 1541

## GWMV2 CRSV1.0-6.5 ADAS features
ID |  | Feature Function Mapping | [5 empty] | Harman Comments （备注）
| Function_ID （功能ID） | Feature-Category (配置-类别) | Feature (特性) | Sub-Feature （子特性） | E/E Function （功能） | Sub-Function （子功能） | Description E/E Function （功能描述）
6.5.8 |  |  |  | RVC |  |  | Rear view camera helps driver to drive backward safetly to protect pedestrains and vehicle from obstacles. 显示界面上可显示后视摄像头的影像及告警信息。
6.5.8.1 |  |  |  | RVC | RVC image display 后视摄像头影像显示 |  | System shall switch current application to RVC when the gear shifts to 'R'. RVC screen shows rear view camera video within 100 msec after switching without any. It is not allowed any flickering during shift P-R-N-D changes repeatedly. System switches back to previous applilcation when gear shifted to other level besides of 'R'. Entertainment audio shall be muted (in case of tuner) or paused (in case of media) and resumed after RVC is deactivated. BT phone hands-free is an exception, keep voice output while RVC is activated. Static and dynamic guidelines shall be controlled by RVC. 当处于倒档时，系统会转换当前路况到倒车后视摄像头。在转换界面之后将在100毫秒内显示后方视野内的录像，而且没有闪屏。在反复切换P-R-N-D档位时不允许有任何的闪屏现象。当换挡时系统会切换到原先的界面，除了倒档。 娱乐音频应当静音（在收音机的情况下）或者暂停（多媒体播放）并且在倒档结束后恢复。蓝牙电话是个例外，当倒档激活时也会一直保持声音输出。倒车状态下的静态与动态引导线是由RVC控制的。
6.5.8.2 |  |  |  | RVC | Warning message display 告警信息显示 |  | Warning message can display on display screen,when the RVC is fault. 当RVC出现故障时，显示界面上会显示相应的告警信息。
|  |  |  | RVC | Trunk open reminder 后备门打开提示 |  | When trunk open,the corresponding reminder will display on screen. 当后备门打开时，在显示界面上会有相应的提示信息。
|  |  |  | RVC | Trailer mode reminder 拖车模式提示 |  | When trailer mode is on,the corresponding reminder will display on screen. 当处于拖车模式时，在显示界面上会有相应的提示信息。
6.5.8.3 |  |  |  | RVC | Popup & Notification handling on RVC 弹出窗口与倒车界面的等级关系 |  | System doesn't allow any popup or notification to block RVC video screen. These shall be displayed after RVC is deactivated. 系统不允许任何的弹窗和通知阻碍RVC的显示屏，在RVC关闭后才可以显示
6.5.8.4 |  |  |  | RVC | Application switching on RVC 源切换在倒车界面的等级关系 |  | System doesn't allow to switch to other screen while RVC is activated, exceptions are when HUT is received PAS or SVC activation requests. 使用RVC时系统不允许切换到其他界面，除非系统收到PAS或者SVC激活的命令。
6.5.9 |  |  |  | PAS |  |  | The image and warning of radar sensor can display on display screen. 显示界面上可显示雷达的信息或告警信息。
6.5.9.1 |  |  |  | PAS | PAS activation/deactivation 倒车辅助功能激活/关闭 |  | When HUT receives PAS activation request through CAN, it switches immeidately to PAS screen. When HUT receives PAS deactivation request through CAN, it switches back to previous application. Manual or semi-auto parking assistant shall be controlled by PAS. 当系统收到PAS激活的请求时，会立即切换到PAS画面，当系统收到PAS结束的请求，会切换回之前的程序。人工或者半自动停车助手由PAS控制。
|  |  |  | PAS | RPAS information display 后雷达信息显示 |  | RPAS image can display on display screen,after RPAS is activated. 当RPAS激活后，可在显示界面上显示后倒车雷达图像。
|  |  |  | PAS | FPAS information display 前雷达信息显示 |  | FPAS image can display on display screen,after FPAS is activated. 当FPAS激活后，可在显示界面上显示前倒车雷达图像。
6.5.9.2 |  |  |  | PAS | APA information display (Auto Parking Assistance System) 半自动泊车辅助系统信息显示 |  | Automatic parking assistant has interactions between HUT and PAS. HUT provides options for user to select vertical or horizontal parking mode, and request automatic parking start and stop. Further detail specification shall be defined later. 当APA激活后，可在显示界面上显示半自动泊车提示图像。
6.5.9.3 |  |  |  | PAS | Voice announcement 语音提示 |  | While PAS is activated and it sends parking guidance voice request to HUT, HUT plays guidance voice through amplifier. The voice shall be in HUT. The list of voice shall be defined by PAS. 泊车辅助时, 后视摄像头进行动静态引导线的引导同时, 进行声音的提示, 该声音设计储存在CD中；在进行动静态引导线时, RVC通过CAN总线发送语音播放指令（GuideVoiceReq ）给CD, CD调取相应的语音播放。每一条指令对应一句话。。
6.5.9.4 |  |  |  | PAS | Error/Exception handling in automatic PAS 在半自动泊车模式下的错误及特殊情况处理 |  | If HUT doesn't receive any signals from PAS, HUT is waiting foit 5 times of defined period and display "Network communication failed. Not available to set." and goes back to previous application automatically. Further description shall be specified later. 如果多媒体在规定时间（5帧）内收不到来自BCM的信号, 则多媒体显示的泊车设置按上一次设置的状态显示,同时弹出提示框“网络通讯故障, 无法设置”。
|  |  |  | PAS | Warning message display 告警信息显示 |  | When the PAS is fault,the corresponding warning message can display on display screen, 当PAS出现故障时，显示界面上会显示相应的告警信息。
6.5.10 |  |  |  | APA |  |  | HUT will support the Autonomous car maneuvering system that moves a vehicle from a traffic lan into a parking spot to perform parallel, perpendicular, angle valet parking. 主机将支持自动车辆操纵系统，其可以讲汽车从车道移动到停车位上，执行平行、垂直、角度的代客泊车。 Display strategy between HUT, HUT and cluster yet to be defined 主机间，主机与仪表间的显示策略有待定义。
6.5.10.1 |  |  |  | APA | Parallel parking 平行泊车 |  | HUT supports method of parking a vehicle parellel to the road in line with other parked vehicles. 主机支持侧方位停车。
6.5.10.2 |  |  |  | APA | Perpendicular parking 垂直泊车 |  | HUT supports perpendicular parking or bay parking, with a method to park the car side by side, perpendicular to Aisle, curb or wall. 主机支持垂直停车或顺次停车，垂直于过道，路边或墙并排停放。
6.5.10.3 |  |  |  | APA | Valet parking 代客泊车 |  | HUT supports valet parking, as a method of safe parking by which infotainment system is restricted for range of distance, Bluetooth pairing disabled and send warning to user by telematics of Vehicle moved away from this range. 主机支持代客泊车，作为安全泊车的一种方式，信息娱乐系统具有距离范围限制，蓝牙配对功能禁止，并通过远程信息处理技术向用户发出偏离出范围的警告。
6.5.11 |  |  |  | SVC |  |  | The image and warning message can display on screen. Side view camera is located on the right side of the vehilce and shows blind spots for driver's safety. 显示界面可显示侧视摄像头的图像和告警信息
6.5.11.1 |  |  |  | SVC | SVC activation/deactivation 侧视摄像头激活/关闭 |  | Case1. When HUT receives gear shift from 'R' to others, it requests SVC activation. It shows SVC screen for 10 seconds and automatically goes back to previous application, before RVC or AVM activated. Case 2. When HUT receives SVC activation request, it requests SVC activation. It shows SVC screen until it receives SVC deactivation request or user shifts gear to R. 点击SVC按键或者退出倒车模式, 激活右前盲区影像；再次点击SVC按键或者车速大于15km/h, 右前盲区功能关闭。
6.5.11.2 |  |  |  | SVC | Speed limits SVC界面的车速限值 |  | When vehicle speed is over 15km/h, system automatically turns off SVC screen and goes back to previous application. Once application is switched, system shall not be back to SVC even vehicle speed is lower then 15km/h. 车速大于15km/h, 自动关闭, 退出SVC画面。
|  |  |  | SVC | Warning message display 告警信息显示 |  | When SVC is fault,the corresponding warning message display on screen. 当SVC出现故障时，在显示界面上显示相应的告警信息。
6.5.12 |  |  |  | AVM |  |  | The image and warning of AVM can display on screen. Around view monitoring system helps driver to park safetly by providing video image from the top or any side of the vehicle. Latency of AVM video screen shall not be exceed 100 msec. 显示界面上可显示环视系统影像和告警信息。
6.5.12.1 |  |  |  | AVM | AVM activation/deactivation 环视摄像头激活/关闭 |  | System shall switch current application to AVM when the gear shifts to 'R'. AVM screen shows rear view camera video within 100 msec after switching without any flickering. It is not allowed any flickering during shift P-R-N-D changes repeatedly. System switches back to previous applilcation when gear shifted to other level besides of 'R'. Entertainment audio shall be muted (in case of tuner) or paused (in case of media) and resumed after AVM is deactivated. BT phone hands-free is an exception, keep voice output while AVM is activated. 当用户挂上倒档的时候，系统会在100ms之内自动从当前程序切换到AVM并且不能有闪屏。连续切换P-R-N-D等档位的时候也不能有闪屏。当摘掉倒档的时候，系统会自动切换回倒档之前的程序。当 AVM激活的时候如果娱乐音频源是收音机的话会静音，如果是多媒体音源的话会暂停，并且AVM结束后会自动恢复。蓝牙电话的情况是个例外，即使AVM激活依然会有声音输出。
6.5.12.2 |  |  |  | AVM | Guidelines for parking setting 环视系统泊车辅助线设置 |  | User can set guidelines for parking display and not display. AVM mudule sends guidelines for AVM wtith composite video signal to HUT. 用户可根据自身需求，设置泊车辅助线的显示和关闭.AVM模块把合成视频引导信号发给主机
6.5.12.3 |  |  |  | AVM | Radar sensors display&distance detection 雷达传感器显示&距离检测 |  | System shall display the vehicle with radar sensors in front and back. When any obstacle is detected, system shall blink detected radar sensor and distance to obstacle 检测到障碍物时，系统应该显示车前后的雷达传感器，检测到障碍物的传感器闪烁并且测量距离障碍物的距离。
6.5.12.4 |  |  |  | AVM | Speed limits of AVM deactivation 关闭AVM界面的车速限值 |  | When vehicle speed is over 15km/h, system automatically turns off AVM screen and goes back to previous application. Once application is switched, system shall not be back to AVM even vehicle speed is lower then 15km/h. 当车速高于15km/h时，系统自动关闭AVM并且回到原先的程序。一旦程序切换，系统不允许回到AVM即使车速低于15km/h.
6.5.12.5 |  |  |  | AVM | Warning message display 告警信息显示 |  | System shall display warning message while AVM is displayed. "Please watch out your surrounding while you're driving" 使用AVM时系统发出警告:驾驶时请注意周边情况。
6.5.12.6 |  |  |  | AVM | Warning message display-Fault 系统故障告警信息显示 |  | When AVM is fault,the corresponding warning message display on screen. 当AVM出现故障时，在显示界面上显示相应的告警信息。
6.5.12.7 |  |  |  | AVM | Change view modes 视角模式切换 |  | System shall provide a method to change AVM view mode as following: 系统提供改变AVM视野的方法如下: - Top View (360 Degrees View) 环视（俯视）: composite view from the top to down.显示从上至下的视野 - Front View 前视: display front camera only. - Rear View 后视: display rear camera only. - Right View 右视: display right camera only. - Left View 左视: display left camera only.
6.5.12.8 |  |  |  | AVM | Popup & Notification on AVM 弹出窗口与环视界面的等级关系 |  | System doesn't allow any popup or notification to block AVM video screen. These shall be displayed after AVM is deactivated. 系统不允许任何的弹窗和通知阻碍AVM的显示屏，在AVM关闭后才可以显示。
6.5.12.9 |  |  |  | AVM | Application switching on AVM AVM源切换在环视界面的等级关系 |  | System doesn't allow to switch to other screen while AVM is activated. 当AVM激活时，系统不允许切换到其他界面。
6.5.12.10 |  |  |  | AVM | Other Display 其他显示信息 |  | When AVM is on,the corresponding image display on screen,because of user's operations,for example:one of four doors is open/outside mirror is folded/rear door is open and so on. 当AVM工作时，由于用户的操作导致的相应的画面提示。例如：四门中任意一门打开、后视镜折叠、后背门打开等。
|  |  |  | AVM |  | Door open reminder 车门打开提示 | When doors open,the corresponding reminder will display on screen. 当任意车门打开时，在显示界面上会有相应的提示信息。
|  |  |  | AVM |  | Trunk open reminder 后备门打开提示 | When trunk open,the corresponding reminder will display on screen. 当后备门打开时，在显示界面上会有相应的提示信息。
|  |  |  | AVM |  | Outside mirror folded reminder 后视镜折叠提示 | When outside mirror is folded,the corresponding reminder will display on screen. 当后视镜折叠时，在显示界面上会有相应的提示信息。
Note on B2: Identification of function用于功能的识别
Note on C2: Specifies the Vehicle Domain Where The Feature belongs To 定义此特性属于哪个域
Note on D2: Vehicle User Description Of activated functions which achieves Specific Aims 基于用户或市场的特征
Note on E2: Vehicle User Description Of activated functions Which are broken down into more detail 由特性分解的子特性
Note on F2: Is Specific Summarized Engineering Electrical & Electronic Function 电子电气相关功能
Note on G2: Is breakdown of Electrical & Electronic Function into smaller manageble functions由功能分解的子功能
Note on H2: Is Simplified description of how the vehicle function works 简洁描述整车功能行为