## Sheet1
ADAS develop plan to Customer Scania
Holiday
| Items | FULL ADAS Package | Scania Package | Start time | Lasting | Owner | Sep 1st ~ Sep 5th | Sep 8th ~ Sep 12th | Sep 15th ~ Sep 19th | Sep 22th ~ Sep 26th | Sep 29th ~ Oct 17th | Oct 20th ~ Oct 24th | Oct 27th ~ Oct 31st | Nov 3rd ~ Nov 7th | Nov 10th ~ Nov 14th | Nov 17th ~ Nov 21st | Nov 24th ~ Nov 27th
| Requirement phase |  |  | 2014-09-01 | 5 | GuoFeng
Task list and API draft for review
| Dependency |  |  | 2014-09-12 | 10
| Hardware platform | J5+V850 J6+V850 IMX6+SH2 | J6+V850 |  |  | Ramanna
| Camera device, ECU etc. | back camera/around camera/front camera/general camera | back camera/front camera/general camera
| Capture package | QNX / HARMAN | QNX
| Screen package | QNX | QNX
| HMI | touch button/legal disclaimer | TBD
| SYSTEM | CAN/Persistency/power control/configuration | TBD
| Layer Manager | graphic layer managerment | TBD
| Diagnosis | video detect/watchdog | TBD
| Hard key | camera mode selection/camera screen switch | TBD
| Performance | Fast ADAS mode | Fast ADAS mode
| Firmware development(ADAS API) |  |  | 2014-09-08
| Graphics | RTA/OPS/Trunk/Warning text | NA |  |  | Liu,Qing
| Camer video | rear/front/side/gerneral/BSCH adjustment | rear/front/side/gerneral |  |  | Liu,Qing
| Guide line | Static/Dynamic | Static |  |  | Liu,Qing
| Automatic extrinsic | surround view | NA |  |  | Yang,Zhen
| Image Undistortion | fish eye/pin hole | NA |  |  | Yang,Zhen/Liu,Qing
Service and Client(Customer ADAS)
| Show/Hide Camera | Show/Hide Camera | Show/Hide Camera |  |  | GuoFeng/Ramanna
| Show/Hide Graphics | Show/Hide Graphics | Show/Hide Graphics |  |  | GuoFeng/Ramanna
| Camera Status communication | Camera Status communication/Camera state chart | Camera Status communication/Camera state chart |  |  | GuoFeng/Ramanna
| Camera parameter adjustment | Camera parameter adjustment | Camera parameter adjustment |  |  | GuoFeng/Ramanna
| Camera Mode Configuration | Camera Mode Configuration | Camera Mode Configuration |  |  | GuoFeng/Ramanna
| Integration |  |  |  |  | Each domain
| Basic ADAS | camera display and basic control of start/ stop | camera display and basic control of start/ stop
| Full ADAS | front camera/reverse camera/general camera/around camera/Graphic/Guide line | front camera/reverse camera/general camera/Guide line
| weeks | [5 empty] | w36 | w37 | w38 | w39 | w40 | w41 | w42 | w43 | w44 | w45
| Note: | work efforts | work effort based on 1.0 man full time per week